SAMPLE MARKETING PLAN

Junior Club Open Day

Marketing objective:	To recruit 20 new junior players to the club by the beginning of the season.

| Marketing Strategies | Cost of Strategies | Time-frame | Responsibility |
| --- | --- | --- | --- |
| Arrange date and time of Free Junior Club Open Day | - | 6 weeks prior to season starting | Marketing Officer/Committee & Junior Coordinator |
| Arrange activities/games at Open Day - free coaching - games/activities - information desk (need welcoming volunteer and forms to record names/phone numbers of those attended) - sausage sizzle (need volunteer) | - Sausages - $25 Buns - $10 Sauce - $5 | 5 weeks prior to season starting | Marketing Officer/Committee & Junior Coordinator |
| Develop a flyer advertising Open Day | Coloured paper - $5 Photocopying costs - $10 | 5 weeks prior to season starting | Marketing Officer/Committee |
| Place flyer on local community notice boards including local shopping centres, library, swimming pool etc. | - | 4 weeks prior to season starting | Marketing Officer/Committee |
| Contact principals of local primary schools to place information in the school newsletter | - | 4 weeks prior to season starting | Marketing Officer/Committee |
| Consider signage – banner to be placed on the club fence on main street | Signage company donated banner and $70 for sign writing | 4 weeks prior to season starting | Marketing Officer/Committee |
| Place information in the club newsletter offering a free soft drink and sausage for those who bring a friend who is not a member to the open day. | Softdrinks - $25 | 2 weeks prior to season starting | Marketing Officer/Committee |
| Write an article and provide a photo for the local newspaper focusing on local junior who joined up at an open day and is now representing the State. | - | 2 weeks prior to season starting | Marketing Officer/Committee |
| Conduct Free Junior Club Open Day | - | 2 weeks prior to season starting | Marketing Officer/Committee & Junior Coordinator |
| Follow-up those who attended but did not join up on the day | $2.50 | 2 weeks prior to season starting | Marketing Officer/Committee & Junior Coordinator |
|  | Total cost = $152.50 |  |  |

Cost Analysis

Actual memberships gained:

22 new members @ $50 recruited = $1,100

Net profit for club $1,100 - $152.50 = $947.50

Evaluation:

Make sure strategies are put in place to check if you have met your

objectives. Some activities are easier to monitor, such as a membership drive,

others will not be able to be evaluated until after the event. Collect copies of

press clippings or media coverage, records of attendances at functions or

competitions and any feedback your club receives whether it’s positive or

negative.